Pre-Launch and Grand-Opening Plan

Document No. AUR-MKT-04 · Version 0.1 (Draft) · Owner: General Manager · Effective: [Date]

1. Purpose

This plan takes The Aura Reset Center from today to a full studio three months after opening. It sets the phases, the founding-100 campaign, the November launch evening, guest lists, budget lines, owners and the numbers we will watch. Dates in square brackets are confirmed by the General Manager once the fit-out handover and Elevé installation dates are fixed.

2. Objectives

1.	Fill the 100 founding-member places before the launch evening.

2.	Open with every Host trained and signed off by Elevé Health on every unit.

3.	Run a calm, flawless soft opening that tests every modality and every booking flow.

4.	Host a launch evening that guests, press and partners remember for how it made them feel.

5.	Reach steady weekly utilisation and membership targets within 90 days.

3. Phases

PHASE 1 — NOW: FOUNDATIONS

Confirm opening date, trade licence and DHA status for IV therapy and hyperbaric oxygen [DHA licence / approval reference].

Activate [Phone], [WhatsApp], [Email], [Instagram]; publish the founding-member list on [Website].

Brief photographer for "Behind the build" content at 332 Jumeirah First.

Agree launch evening date, guest list owners and budget.

PHASE 2 — FOUNDING LIST OPEN

Founding-100 campaign live (section 4).

Weekly social calendar running (AUR-MKT-05).

Corporate partner and wellness creator outreach begins.

PHASE 3 — HOSTS TRAINED

Elevé installation and calibration complete; units signed off to clinical spec.

Elevé host training on all units; each Host signed off per modality.

Clinical Lead completes IV protocols and DHA readiness.

Internal "friends and family" sessions to rehearse flows: arrival, breathing ritual, screening, each modality, checkout.

PHASE 4 — SOFT OPENING

[3–7] days, founding members first, limited slots per time band.

Every guest asked for feedback; daily stand-up to fix issues.

Booking software, payment provider and invoices tested end to end.

PHASE 5 — NOVEMBER LAUNCH EVENING

Official opening (section 5).

PHASE 6 — FIRST 90 DAYS

Convert founding list and launch guests to memberships.

Guest-pass conversion and referral programme live (AUR-MKT-07).

Monthly review of KPIs; adjust time bands, staffing and content.

4. Founding-100 campaign

Offer (from website): launch price locked for 12 months; two guest passes every month for the first three months; invitation to the November launch evening; first choice of opening-week sessions. No payment taken on joining the list.

Message: "A recovery studio for the modern nervous system, opening in Jumeirah 1. The first 100 are welcomed first."

Channels:

Website founding-member form and a counter showing places remaining [if approved].

Instagram and TikTok: Behind the build, Meet the hosts, Founder story.

LinkedIn: Elevé partnership, corporate wellness.

WhatsApp broadcast to the list, with consent.

Founder and CEO personal networks.

Wellness creators invited to a preview.

Mechanics:

1.	Guest joins list; confirmation email with founding-member number.

2.	Host or General Manager calls or messages within [48] hours to welcome and answer questions.

3.	Launch evening invitation sent [3] weeks before.

4.	Opening-week session choice offered in sign-up order.

5.	Membership activated at first visit; locked price recorded in the booking system.

5. Launch evening run-of-show

Date: [Date], November 2026 · Venue: The Aura Reset Center, 332 Jumeirah First · Capacity: [___] guests

| Time | Moment | Detail | Owner |
| --- | --- | --- | --- |
| [T −4h] | Final set-up | Lighting, aura-ring installation, sound, scent, catering set, rooms reset | General Manager |
| [T −1h] | Team briefing | Run-of-show, room stations, safety, consent wristbands for photography | General Manager |
| T | Arrival | Welcome by Hosts, robes-optional tour route, non-alcoholic welcome drink | Lead Host |
| T +20 | Opening breath | Whole room: "In for four, out for six", led by breathwork guide | Breathwork guide |
| T +30 | Welcome words | Founder & CEO, then CEO; Elevé Health representative | Founder & CEO |
| T +45 | Studio experiences | Short demos at stations: red-light bed, compression, salt cabin, dry float. No cold or HBOT sessions for guests on the night [to be confirmed] | Hosts |
| T +45 | Elevé tech corner | Elevé team explains installation and calibration standard | Elevé Health |
| T +90 | Founding-member moment | Founding members recognised; opening-week booking desk open | General Manager |
| T +120 | Close | Gift bag, thank-you, follow-up message within 24 hours | Lead Host |

Safety: no guest uses cryotherapy, cold plunge, hyperbaric oxygen or IV therapy on the night. Photography only of guests wearing a consent wristband. First aid and fire marshal named [Name].

6. Guest list categories

| Category | Who | Target number | Owner |
| --- | --- | --- | --- |
| Founding members | First 100 on the list, plus one guest [if capacity] | [___] | General Manager |
| Press | Lifestyle, wellness and business media in the UAE | [___] | [PR agency / Marketing lead] |
| Wellness creators | Creators aligned with calm, wellness and Dubai lifestyle; no hype-led accounts | [___] | [Marketing lead] |
| Corporate partners | HR and wellbeing leads from target companies, hotels, airlines | [___] | CEO |
| Elevé team | Elevé Health leadership, technicians and trainers | [___] | Founder & CEO |
| Friends of The Aura | Landlord, contractors, advisers, neighbours | [___] | Founder & CEO |

7. Budget lines

| Line | Phase | Budget | Owner |
| --- | --- | --- | --- |
| Photography and video (build, hosts, launch) | 1–5 | AED [___] | Marketing lead |
| Paid social (founding-100) | 2 | AED [___] | Marketing lead |
| PR agency or freelance support | 2–5 | AED [___] | CEO |
| Creator preview sessions (cost of sessions) | 3–4 | AED [___] | General Manager |
| Print and signage (invitations, menus, wayfinding) | 3–5 | AED [___] | General Manager |
| Launch evening: catering and non-alcoholic drinks | 5 | AED [___] | General Manager |
| Launch evening: lighting, sound, styling | 5 | AED [___] | General Manager |
| Gift bags | 5 | AED [___] | General Manager |
| Staffing (extra hours, security, valet) | 5 | AED [___] | General Manager |
| Contingency ([10]%) | All | AED [___] | CEO |
| Total |  | AED [___] | CEO |

Spending follows the delegation of authority (AUR-GOV-02) and purchasing procedure (AUR-FIN-10).

8. Owners

| Area | Accountable | Supports |
| --- | --- | --- |
| Overall plan and budget | CEO | Founder & CEO |
| Brand, story, Elevé relationship | Founder & CEO | CEO |
| Day-to-day delivery, studio readiness, launch evening | General Manager | Lead Host |
| Social and content | [Marketing lead] | Hosts |
| Clinical readiness (IV, screening) | [Clinical Lead] | General Manager |
| Host training sign-off | Elevé Health | General Manager |

9. KPIs

| KPI | Target | Measured |
| --- | --- | --- |
| Founding list sign-ups | 100 before launch evening | Weekly |
| Founding list to paid membership conversion | [___]% within 30 days of opening | Monthly |
| Launch evening attendance vs RSVPs | [___]% | Once |
| Press pieces published | [___] in first 30 days | Monthly |
| Instagram followers / reach | [___] / [___] by opening | Weekly |
| Weekly sessions booked | [___] by day 90 | Weekly |
| Utilisation by modality | [___]% average by day 90 | Weekly |
| Guest-pass to first paid visit conversion | [___]% | Monthly |
| Active members | [___] by day 90 | Monthly |
| Guest satisfaction | [___] average rating | Monthly |

10. Timeline

| Phase | Window | Key milestone | Owner | Status |
| --- | --- | --- | --- | --- |
| 1. Foundations | [Date] – [Date] | Channels live; founding list published | General Manager | ☐ |
| 2. Founding list open | [Date] – launch evening | 100 sign-ups | Marketing lead | ☐ |
| 3. Hosts trained | [Date] – [Date] | Elevé sign-off on all units and Hosts | General Manager | ☐ |
| 4. Soft opening | [Date] – [Date] | All flows tested with founding members | General Manager | ☐ |
| 5. Launch evening | [Date], November 2026 | Official opening | Founder & CEO | ☐ |
| 6. First 90 days | Opening – [Date] | KPI targets met; review | CEO | ☐ |